## Overview
Sara-Arch — Action Plan & Health Check
Item | Value
Live Version | v289
Branch | main
Date | 2026-07-06
Unit Tests | 18 passed / 18
Lint | 0 errors, 35 warnings
npm audit | 4 vulnerabilities (2 moderate, 1 high, 1 critical) — dev deps
Deploy Status | Green (last run success)
Daily Backup | Running successfully
Top Risk | Exposed active GitHub OAuth token + owner GitHub 2FA disabled
Summary
The app is stable and the core security fixes (tenant isolation, RLS, view security_invoker) are in place.
The highest-priority risks are active account-security issues (exposed token, disabled 2FA/MFA) and financial-calculation correctness (supervision, balance math, retention).
The new v289 "email new password" feature is deployed but requires Resend settings to be inserted manually.

## Do Now (24h)
Do Now — Next 24 hours
# | Task | Area | Priority | Acceptance Criteria | Status | Notes
0.1 | Revoke exposed GitHub OAuth token immediately | Security | Critical | Old token returns 401 / no longer listed in GitHub tokens | Pending | Active incident; do not wait for a phase
0.2 | Enable GitHub 2FA on Gendy92 owner account | Security | Critical | 2FA status enabled in GitHub settings | Pending | Prevents account takeover
0.3 | Enable MFA for admin users in Supabase Auth | Security | Critical | All admin accounts enrolled in TOTP/phone MFA | Pending | Auth -> Providers/MFA
0.4 | Insert Resend key + sender into app_settings and send test email | Feature | High | Test user receives new password email | Pending | Use Supabase SQL Editor
0.5 | Run verify_high_priority.sql + tenant_isolation.sql + check Security Advisor UI | Security | Critical | Zero high/medium Security Advisor warnings | Pending | Manual Supabase step

## Phase 1 - This Week
Phase 1 — This week
# | Task | Area | Priority | Acceptance Criteria | Status | Notes
1.1 | Design decision: supervision system-locked audit row | Architecture | High | Decision doc agreed; implementation ticket created | Pending | See docs/DECISION_supervision_audit_row.md
1.2 | Design decision: retention / holdback model | Architecture | High | Decision doc agreed; implementation ticket created | Pending | See docs/DECISION_retention_holdback.md
1.3 | Add UI input validation to block paid_amount > amount before save | UX/Quality | High | Save button disabled / inline error when paid > amount | Pending | Do not rely only on server-side rejection
1.4 | Add unit tests for balance, supervision, and payroll math | Quality | High | Core calculation paths covered; CI green | Pending | Silent financial bugs are client-facing errors
1.5 | Patch vitest/vite/esbuild vulnerabilities | Quality | High | npm audit returns 0 high/critical | Pending | Dev-only but should be clean
1.6 | Fix ESLint warnings (npm run lint:fix + manual review) | Quality | Medium | npm run lint shows 0 warnings | Pending | 35 warnings currently
1.7 | Protect main (and dev.2) with required status checks | DevOps | High | Cannot push directly; PRs require CI pass | Pending | Branch protection rules
1.8 | Fast-forward or delete dev.2 | DevOps | Low | main and dev.2 are not diverged | Pending | dev.2 is 6 commits behind

## Phase 2 - Short Term
Phase 2 — Short Term (next 2–4 weeks)
# | Task | Area | Priority | Acceptance Criteria | Status | Notes
2.1 | Implement retention / holdback tracking | Product | High | Retention withheld/released per project; reports correct | Pending | Often contractually required
2.2 | Generate system-locked supervision audit rows (if decided) | Product | High | System rows appear at period close; non-editable; tagged | Pending | Depends on 1.1 decision
2.3 | Add Items catalog UI | Product | High | Screen lists/CRUD items table | Pending | Code exists, no UI
2.4 | Add Custody expenses UI | Product | High | Direct custody expense entry | Pending | Currently tracked by returned_amount only
2.5 | Add Employee transactions UI | Product | High | Add/edit advances, penalties, bonuses | Pending | Only consumed in payroll now
2.6 | Add Salary history UI | Product | Medium | Screen shows employee_salary_history | Pending | Table exists, no UI
2.7 | Build real Settings page | Product | High | Configure currency, logo, default supervision | Pending | Currently placeholder
2.8 | Implement restore-from-backup | Product | High | Upload ZIP/JSON and import tables | Pending | Backup is export-only
2.9 | Add server-side pagination + indexes | Performance | High | Large lists load <1s | Pending | transactions, clients, vendors
2.10 | Update outdated docs (TEST_PLAN, TEST_DATA, APP_TABS_GUIDE, ROADMAP) | Docs | Medium | Docs match current runtime | Pending | Target v83/v105 references
2.11 | Set up staging Supabase + monthly restore test | DevOps | High | Successful restore verified monthly | Pending | DR proof
2.12 | Rotate Supabase service-role and anon keys | Security | High | New keys in GitHub Secrets; old keys disabled after CI passes | Pending | Periodic rotation

## Phase 3 - Medium Term
Phase 3 — Medium Term (1–3 months)
# | Task | Area | Priority | Acceptance Criteria | Status | Notes
3.1 | Invoicing module with PDF export | Product | High | Create, number, status workflow, PDF export | Pending
3.2 | Inventory / stock tracking | Product | High | Procurements affect quantity on hand | Pending
3.3 | P&L, aging, cash-flow reports | Reporting | High | New report screens with accurate totals | Pending
3.4 | Document attachments via Supabase Storage | Product | Medium | Upload/link files to clients/projects/transactions | Pending
3.5 | Notifications / alerts (overdue, deadlines, low stock) | Product | Medium | Users see alert badges/notifications | Pending
3.6 | PWA offline fallback + background sync queue | UX | Medium | App works offline and syncs when online | Pending

## Phase 4 - Long Term
Phase 4 — Long Term
# | Task | Area | Priority | Acceptance Criteria | Status | Notes
4.1 | Evaluate migration to frontend framework (React/Vue/Svelte) | Architecture | Low | Decision documented with PoC | Pending
4.2 | Move more business logic to DB triggers / Edge Functions | Architecture | Medium | Supervision, balances, payroll computed server-side | Pending
4.3 | End-to-end tests with Playwright | Quality | Medium | Critical flows automated | Pending
4.4 | Split crud.js and app-loaders.js into per-module files | Maintainability | Low | Modular file structure | Pending

## Test Results
Latest Test & Audit Results (2026-07-06)
Check | Result | Details
npm test (Vitest) | Pass | 3 test files, 18 tests, 0 failed
npm run lint | Warning | 0 errors, 35 warnings (unused vars, == vs ===, let vs const)
npm audit | Fail | 4 vulnerabilities in dev deps: esbuild moderate, vite moderate/high, vitest critical
GitHub Actions pages.yml | Pass | Last deploy run success
GitHub Actions ci.yml | Pass | Last lint/test run success
GitHub Actions backup.yml | Pass | Daily scheduled backups success
Supabase Security Advisor | Pending | Run verify_high_priority.sql + UI check
Tenant isolation SQL test | Pending | Run tests/tenant_isolation.sql
Acceptance checklist | Pending | Manual browser run (AUTH + USR items blocked)